## Project Overview
ARTIC Project Toolkit ¦ Ready-to-Use Tools and Templates
ARTIC Project Planning and Engagement Workbook
How to use this workbook: This is a single living file for one project. Fill in what you know on this Project Overview, then use the four working tabs (Project Notices, Stakeholder and Agency Contacts, Engagement Timeline, Funding Opportunities) as the project moves forward. The Funding Directory tab at the end is a reference list only. Yellow cells are for you to fill in. Blue cells fill in on their own from the other tabs; you do not need to type in them. Keep one copy in a shared location so it survives staff and leadership changes.
Project basics
Project name
Project type
Brief description
Location and affected communities
Developer or project sponsor
Lead federal agency
Other involved agencies
Current project phase
Internal responsibility
Tribe, ANC, or organization
Internal project lead
Leadership or governing body responsible
Other staff or partners involved
Current snapshot
Current status
Next major milestone
Next dated milestone (fills in from the Engagement Timeline tab) | None entered
Date of that milestone (fills in from the Engagement Timeline tab) | None entered
Next known deadline
Next response deadline (fills in from the Project Notices tab) | None entered
Notices still open or in progress (fills in from the Project Notices tab) | 0
Next scheduled meeting or engagement
Immediate action needed
Current community position, if established (see Tool 12)
Date last updated
Workbook use
Person responsible for maintaining the workbook
Date the workbook was created
Links or references to the main project folder and key documents

## Project Notices
ARTIC Project Toolkit ¦ Ready-to-Use Tools and Templates
Tool 7: Project Notice Tracking Sheet
How to use this tool: Use one row per notice, not one row per project. A single project generates multiple notices over its lifecycle. Log each notice the day it arrives, set the response deadline, and assign a person. Use the filter arrows to sort by deadline or status.
Project details are on the Project Overview tab.
Legend: yellow cells are for you to fill in. Row 9 is an example; type over it or delete it. Use the filter arrows in the header row to sort and filter.
Project name | Agency / lead | Notice type | Date received | Response deadline | Status | Assigned to | Notes
Example: Kuskokwim Road Project | BLM Alaska State Office | NEPA scoping notice | 2026-10-05 | 2026-11-04 | Open | J. Smith | Scoping meeting in village on Oct. 20; comment letter drafted by Oct. 28

## Stakeholder and Agency Contacts
ARTIC Project Toolkit ¦ Ready-to-Use Tools and Templates
Tool 8: Stakeholder and Agency Contact Worksheet
How to use this tool: Update this sheet whenever staff turnover is identified. Turnover at agencies is one of the most common ways continuity gets lost between meetings. Record every agency, developer, and partner contact, what authority they hold, and when you last spoke.
Project details are on the Project Overview tab.
Legend: yellow cells are for you to fill in. Row 9 is an example; type over it or delete it. Use the filter arrows in the header row to sort and filter.
Name | Organization / agency | Role / authority | Type | Phone | Email | Last contact | Notes
Example: Jane Doe | BLM Alaska State Office | Realty specialist; prepares ROW recommendation | Agency | 907-555-0100 | jdoe@example.gov | 2026-09-15 | Prefers email; new in role as of Aug. 2026

## Engagement Timeline
ARTIC Project Toolkit ¦ Ready-to-Use Tools and Templates
Tool 9: Project Engagement Timeline
How to use this tool: Map out a project's key dates as they become known: a single place to see engagement windows before they close. Standard milestones are listed first; add your own rows below them. Mark whether each milestone is an engagement opportunity and what you plan to do.
Project details are on the Project Overview tab.
Legend: yellow cells are for you to fill in. Row 9 is an example; type over it or delete it. Use the filter arrows in the header row to sort and filter.
Milestone | Expected date | Actual date | Engagement opportunity? (Y/N) | Our planned action | Responsible | Status | Notes
Example: NEPA scoping period | 2026-10-05 |  | Y | Submit scoping comments; request consultation | J. Smith | Planned | Deadline Nov. 4
Project first identified
Pre-application / pre-scoping
NEPA scoping period
Consultation requested
Draft document / comment period
Final decision expected
Construction season window

## Funding Opportunities
ARTIC Project Toolkit ¦ Ready-to-Use Tools and Templates
Tool 11: Funding Search Worksheet
How to use this tool: Use alongside the Funding and Technical Assistance Directory to track what's been identified and applied for. Type each program you find on its own row. For the programs already described in the Toolkit, you can pick the name from the dropdown in the Program name column and the Agency and Website columns will fill in for you (they are listed on the Funding Directory tab for reference). Remember: match requirements and competitive-grant disadvantages are real structural barriers for smaller communities, but don't assume a program is unusable without first checking whether match can be met through in-kind contribution or partnership.
Project details are on the Project Overview tab.
Legend: yellow cells are for you to fill in. Row 9 is an example; type over it or delete it. Use the filter arrows in the header row to sort and filter. Blue cells fill in on their own when you pick a Toolkit program from the dropdown; for any other program, type the agency and website in yourself.
Program name | Agency | Eligible? (Y/N/Unsure) | Deadline | Match required? | Amount requested | Status | Website | Notes
DOE Office of Indian Energy: Unleashing Tribal Energy Development | U.S. Department of Energy, Office of Indian Energy Policy and Programs | Y | 2027-02-15 | Yes, 20% (in-kind allowed) | 250000 | Preparing application | https://www.energy.gov/indianenergy | Example row: confirm the current deadline with the program before relying on this date

## Funding Directory
ARTIC Project Toolkit ¦ Ready-to-Use Tools and Templates
Funding Directory (reference list)
Reference only. This tab lists the federal programs described in the Funding and Technical Assistance Directory section of the ARTIC Project Toolkit, so you do not have to retype them. Track your funding search on the Funding Opportunities tab: type any program there, or pick one of these programs from the dropdown to fill in the agency and contact automatically. You do not need to add anything to this tab. Funding programs change often, so always confirm current details directly with the program.
Category | Program name | Administering agency | Eligible applicants | Types of projects supported | Applicable project stage | Technical assistance | Website | Application notes
Energy | DOE Office of Indian Energy: Unleashing Tribal Energy Development | U.S. Department of Energy, Office of Indian Energy Policy and Programs | Indian Tribes (including Alaska Native Regional and Village Corporations), intertribal organizations, Tribal Energy Development Organizations, Tribal Colleges and Universities | Community-scale energy project planning and development; large-scale commercial energy project pre-development | Pre-development and planning through construction, depending on topic area | DOE Office of Indian Energy offers no-cost technical assistance separate from this funding opportunity: education, technical/financial analysis, and strategic energy planning | https://www.energy.gov/indianenergy
Energy | DOE Office of Indian Energy: Ongoing Technical Assistance Program | U.S. Department of Energy, Office of Indian Energy Policy and Programs | Tribes and Alaska Native entities pursuing self-defined energy goals | No-cost technical, financial, and strategic planning assistance for energy projects (not project funding) | Any stage, especially early planning | This program is the technical assistance | https://www.energy.gov/indianenergy
Water, Sanitation, and Basic Infrastructure | USDA Rural Alaska Village Grants (Village Safe Water Program) | USDA Rural Development, Rural Utilities Service, in partnership with Alaska DEC and the Alaska Native Tribal Health Consortium (ANTHC) | Rural or Native villages in Alaska, or the State of Alaska/ANTHC on behalf of a village | Water and wastewater system development and construction to address dire sanitation conditions | Planning through construction | ANTHC and Alaska DEC provide direct technical support alongside grant funding | https://www.rd.usda.gov | Water and Environmental Programs; applications accepted year-round through the local Rural Development office
Water, Sanitation, and Basic Infrastructure | USDA Rural Community Development Initiative Grants | USDA Rural Development | Non-profit housing and community development organizations, low-income rural communities, federally recognized Tribes | Housing, community facilities, community and economic development | Planning and capacity-building, typically feeding into a later construction grant |  | https://www.rd.usda.gov
Housing and Community Development | HUD Indian Community Development Block Grant (ICDBG) | HUD Office of Native American Programs | Federally recognized Tribes and Alaska Native villages (or an authorized tribal organization applying on their behalf) | Two tracks: Single Purpose grants (housing, community facilities, infrastructure, economic development; competitive) and Imminent Threat grants (non-competitive, for urgent public health/safety issues) | Planning through construction | HUD's Office of Native American Programs regional office can advise on application preparation | https://www.hud.gov/helping-americans/public-indian-housing-grants-icdbg | Single Purpose grants run on an annual funding cycle. Imminent Threat applications are accepted on a rolling basis directly to ONAP-ICDBG@hud.gov, not through Grants.gov
Economic Development and Business | EDA Public Works and Economic Adjustment Assistance (PWEAA) | U.S. Economic Development Administration, Department of Commerce | Indian Tribes or a consortium of Tribes, among other eligible entities | Construction, non-construction, planning, technical assistance, and revolving loan fund projects supporting regional economic development strategy | Planning through construction | EDA's Office of Tribal Economic Development has a dedicated Tribal Engagement Coordinator (indigenous@eda.gov); EDA strongly encourages pre-application consultation with the assigned Economic Development Representative for Alaska before submitting | https://www.eda.gov/funding/programs/public-works | Contact the Tribal Engagement Coordinator at indigenous@eda.gov; consult the Economic Development Representative for Alaska before submitting
Economic Development and Business | USDA Rural Business Development Grant (RBDG) | USDA Rural Development, Rural Business-Cooperative Service | Public bodies, Indian Tribes, nonprofits primarily serving rural areas | Business opportunity and business enterprise grants supporting economic development and job creation | Planning and early-stage business development | Not a separate track; built into award structure. Smaller requests are prioritized | https://www.rd.usda.gov | No required match
Planning-Stage and Study Funding | Denali Commission Project Support | Denali Commission | Varies by program; the Commission has directly supported state, borough, and Tribal infrastructure planning efforts | Early-stage study and planning work (for example, support for the Triangle Community Road Planning and Environmental Linkage study) | Planning stage, before construction and before federal environmental review begins | Contact the Commission directly to discuss what's available for a specific project | https://www.denali.gov